## SHLS Sample Workplan
Annex 2.1 SHLS Workplan
Sector(s):
Grant:
Location: |  |  |  | 3 months
Workplan |  |  | Responsible | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
Location X | Progress | PMD Officers |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
Step 1 - Context Analysis and Needs Assessment
Secondary data collection | bar: Month 1 Wk 1
Primary data collection | bar: Month 1 Wk 1 to Month 1 Wk 2
Team discussion and analysis | bar: Month 1 Wk 1 to Month 1 Wk 2
Step 3 - Budget and Procurement Plan
Budget development | bar: Month 1 Wk 2
Procurement plan development | bar: Month 1 Wk 2
Step 4 - Location and Set-Up
Identification of site with involvement of the community | bar: Month 1 Wk 2
Safety mapping and risk assessment | bar: Month 1 Wk 2; Month 2 Wk 2; Month 3 Wk 2
Infrastructure set up | bar: Month 1 Wk 2 to Month 1 Wk 4
Step 5 - Human Resources
Post positions | bar: Month 1 Wk 2 to Month 1 Wk 3
Recruit | bar: Month 1 Wk 3 to Month 1 Wk 4
Staff training | bar: Month 1 Wk 4 to Month 3 Wk 1
Step 6 - Defining Program Content
Contextualization of the curricula selected for the intervention | bar: Month 1 Wk 3 to Month 2 Wk 1
Jointly develop the daily SHLS schedule with community stakeholders (including children and youth) | bar: Month 2 Wk 2
Step 7 - M&E
M&E strategy development | bar: Month 1 Wk 2 to Month 1 Wk 4
M&E tools adaptation | bar: Month 1 Wk 3 to Month 1 Wk 4
M&E tools testing | bar: Month 1 Wk 4 to Month 2 Wk 1
Team training on data collection | bar: Month 2 Wk 1 to Month 2 Wk 2; Month 3 Wk 2
ASER Training | bar: Month 2 Wk 2
Ongoing monitoring | bar: Month 1 Wk 3 to Month 3 Wk 4
Step 8 - SHLS Committees
Set up of Parents' and Children's committees | bar: Month 2 Wk 2
Regular meetings | bar: Month 2 Wk 3 to Month 3 Wk 4
Step 9 - Feedback mechanisms
Set up Feedback mechanisms | bar: Month 2 Wk 2 to Month 3 Wk 4
Step 10 - Developing SHLS referral pathways
Development of referral pathways | bar: Month 1 Wk 3 to Month 2 Wk 1
Step 11 - Starting activities
Community awareness on the services available at the SHLS | bar: Month 2 Wk 1 to Month 2 Wk 3
Registration of children and caregivers | bar: Month 2 Wk 2 to Month 2 Wk 3
Implement the activities | bar: Month 2 Wk 2 to Month 3 Wk 4
Step 12 - Transition and Exit
Based on continued need for the program and funding availability