The following is a brief example of what a Feedback Plan in a camp setting with moderate to high coverage of cellphones could look like. It is not meant as the only option for a Feedback Plan, but only as a starting point, to be adapted as relevant in each response.

Start Date: Jan 1

| Phase | Description | Action Points | Responsible/Time |
| --- | --- | --- | --- |
| Set-up: Methods, tools, staff training, publicize | A combination of active and static methods will be used as follows: - Locked, marked, “Suggestion/Concern” boxes at all service delivery points (health clinics, schools, IRC office, etc) - Dedicated cell phone carried by X. Turned on to receive calls and SMS during office hours only. - Help Desk with complaint forms at all distributions. - Three beneficiary satisfaction questions added into all project monitoring tools - Monthly open camp meeting (where suggestions are given, and responses to previous suggestions are supplied) | - Procure, mark and place the required 5 boxes. - Procure dedicated cell phone - Publicize cell phone number - Train X on feedback and tracking tools and protocol and protection - Modify monitoring tools - (Optional) Modify tracking sheet to accommodate the 3 satisfaction questions - Arrange standing monthly meeting in each camp - Publicize monthly meeting - Identify staff for community monthly meetings | Logs- Jan 10 Logs- Jan 5 Logs + field team Jan 15 Team Leader- Jan 5 Prog Cos- Jan 10 Team Leader + X -Jan 15 Prog Cos- Jan 20 Field staff- Jan 25 Prog Cos- Jan 20 |
| Receive: Use, track | - Beneficiaries submit suggestions into the locked boxes - Beneficiaries call or SMS their concerns - Help desk concerns are addressed as they arise. - Program coordinators and/or field staff use monitoring tools in programing and gain satisfaction data - Notes are taken (in the tracking tool format) at each monthly meeting | - Boxes are checked 1/week and all suggestions logged in tracking tool - Calls and SMS are logged in tracking tool daily - Any unresolved help desk claims are submitted to X at the end of the day for entrance onto the tracking tool - Satisfaction data analyzed by program coordinators - Notes from monthly meetings are provided to X for entrance onto the tracking tool | X – 1/week X- 1/day Field staff- 1/distribution Prog Cos- 1/month Prog Cos/field staff- 1/month |
| Respond Refer, Address | - Beneficiaries receive a timely response to their suggestions, complaints and feedback | - Team Leader creates referral guidelines and trains X - X moves all new feedback in tracking tool to the appropriate referral sheet - Program Coordinators and Team Leader review their referrals, address them, and update their tracking sheet - Camp meetings address all issues noted in the tracking tool as “community response” - Team Leader reviews tracking tool, noting feedback vs redressal, and follows up on any gaps | Team Leader- Jan 5 X -1/week Prog Cos + Team Lead- 1/week Prog Cos + field staff – 1/month Team Leader – 1/month |

Sample Referral Guidelines

The following feedback topics should be referred to the noted IRC staff member:

Follow Global SPC System

- Feedback/concerns regarding X type of programs

IRC X Program Coordinator

- Security concerns

- Mistreatment of a beneficiary

- Fraud

- All “sensitive” claims

- Concerns with logistics, finance or vehicles

- Other miscellaneous claims

SPC related claims

IRC Team Leader

IRC Z Program Coordinator

- Feedback/concerns regarding Z type of programs

- Feedback/concerns regarding Y type of programs

IRC Y Program Coordinator

“X” is the same as the “focal point” in the Feedback Protocol and can be one or two persons. As noted in the protocol, the three priority skills for this person are 1) as independent from programs as possible (possibly an admin officer), 2) speak one or more local languages, 3) have the capacity to be trained on the use of the feedback tracking tool (in excel). Depending on the volume of feedback this role may be expected to take 2 to 5 hours per week.

It is suggested that a separate dropbox for the feedback tracking tool is created, with access given only to X and those who will address the feedback. This will minimize the need to merging of multiple spreadsheets, and help protect confidentiality.

Alternatively Program Coordinators may track and utilize the data. However, if the three questions are standard across programs, data should be compiled at least twice a year to understand the overall trends and changes in satisfaction and concerns.